## Sheet1
Task | Start Week | Week to Complete
Project Selection and Problem Analysis | 0 | 1
Feasibility Analysis | 1 | 1
Data Collection & Analysis | 2 | 1
Data Flow & use CASE diagram | 3 | 1
Entity Relation Diagram | 4 | 1
Class Diagram | 4 | 1
Sequence & Collaboration Diagram | 5 | 1
Data host & Domain Server | 6 | 1
UX/UI Design (Physical Design) | 6 | 1
Logical Design | 6 | 1
Frontend Develop | 7 | 2
Data Entry | 7 | 1
Backend Develop | 8 | 2
Backend & Frontend Collaboration | 10 | 1
Deploy to web server | 11 | 1
Testing & final Presentation | 12 | 1