## project
Activity Schedule
[7 empty] | Period Highlight: |  |  |  |  | 13 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | Slack
|  | PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
ID | Task Name | START | DURATION | START | DURATION | COMPLETE | PERIODS
|  | in Week | in weeks |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1 | Project Selection & Problem Analysis | 1 | 1 | 1 | 1 | 100%
2 | Feasibility Analysis | 2 | 1 | 2 | 1 | 100% | bar: PERIODS 1 to PERIODS 2
3 | Data Colletion & analysis | 3 | 1 | 3 | 1 | 100%
4 | Data flow & use CASE Diagram | 4 | 1 | 4 | 1 | 100%
5 | Entity Relationship Diagram | 5 | 1 | 5 | 1 | 100%
6 | Class Diagram | 5 | 1 | 5 | 1 | 100%
7 | Sequence & Collaboration Diagram | 6 | 1 | 6 | 1 | 100%
8 | Data Hosting & Domain Server Setup | 7 | 1 | 7 | 5 | 100% | PERIODS 9: 4 weeks
9 | UX/UI design (Physical Design) | 7 | 1 | 7 | 2 | 100% | PERIODS 8: 1 week
10 | Logical Design | 7 | 1 | 7 | 1 | 100%
11 | Frontend Develop | 8 | 2 | 8 | 3 | 100% | PERIODS 10: 1 week
12 | Data Entry | 8 | 1 | 8 | 1 | 100% | bar: PERIODS 8
13 | Backend Develop | 9 | 2 | 9 | 2 | 100%
14 | Backend & Frontend Collaboration | 11 | 1 | 11 | 1 | 100%
15 | Deploy to web server | 12 | 1 | 12 | 1 | 100%
16 | Testing & Final Presentation | 13 | 1 | 13 | 1 | 100%